## general_report
Spendsy
Displaying 142 issues at 03/Aug/16 3:05 PM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Account | Business Value | Epic Color | Epic Link | Epic Name | Epic Status | Epic/Theme | Flagged | Iteration | Raised During | Rank | Sprint | Story Points | Team | Test Sessions | Testing Status | [CHART] Date of First Response
Spendsy | SPEN-144 | Account balance only decreases for each transaction update | Bug | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-12-17 17:27 | 2016-08-03 15:04 | 2014-12-17 17:28 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | When a transaction is updated, the account balance should be increased by the old and amount and decreased by the new amount. There is code for this in app/controllers.py, but it seems to be broken. | [7 empty] | None | [7 empty] | None |  | 0¦1000vs: |  |  | None |  | Not started
Spendsy | SPEN-143 | Set up spendsy staging server | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-12-02 14:10 |  | 2014-12-03 15:42 | 2014-12-03 15:42 |  |  | DevOps |  | 0 | 1 | [8 empty] | The server instance has already been created. Need to install all dependencies: git pip mongodb nginx The domain staging.spendsy.me is already pointed to 130.211.144.25, so once the dependencies are installed, this vm will be used to test code changes where the server will remain on the 'staging' branch in the git repo. Change the git branch on the production server to 'master'. | [7 empty] | None | [7 empty] | None |  | 0¦1000vk: |  |  | None |  | Not started
Spendsy | SPEN-142 | Purchase iStockPhoto credits | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-12-02 11:10 |  | 2014-12-02 11:10 |  |  |  | Admin |  | 0 | 1 | [8 empty] | https://secure.istockphoto.com/checkout/credits Purchase 18 credits for $136 using promo code CREDITS20 before December 5th! | [7 empty] | None | [7 empty] | None |  | 0¦1000vc: |  |  | None |  | Not started
Spendsy | SPEN-141 | SPEN-140 Create feedback@spendsy.me email address | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-30 16:48 |  | 2014-12-02 11:16 | 2014-12-02 11:14 |  |  | Admin |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000v4: |  |  | None |  | Not started
Spendsy | SPEN-140 | Add heading to each app page letting user know that Spendsy is in beta | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-30 16:46 |  | 2014-11-30 16:53 |  |  |  | Web Application |  | 0 | 1 | [5 empty] | SPEN-141 | SPEN-119 |  | Text should read, "Spendsy is in beta development. If you don't see a feature or functionality you would like or expect, please email us at feedback@spendsy.me or check back for updates" | [7 empty] | None | [7 empty] | None |  | 0¦1000uw: |  |  | None |  | Not started
Spendsy | SPEN-139 | Burnrate shows negative amount for days passed | Bug | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-29 14:49 |  | 2014-11-29 20:19 | 2014-11-29 20:19 |  |  | API |  | 0 | 1 | [8 empty] | Burnrate shows a negative days_passed value if the span between now and the next pay date is greater than the totals days of the pay cycle. To fix this, take the absolute value of the negative days_passed value and add it to the total days for that pay period so it will cover the whole pay period and catch all transactions for that pay period. | [7 empty] | None | [7 empty] | None |  | 0¦1000uo: |  |  | None |  | Not started
Spendsy | SPEN-138 | Accounts can all be set to 'iscurrent' | Bug | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-27 11:09 |  | 2014-11-27 11:09 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | When updating an account, even if the user doesn't select to make the account being edited the currrent account, the account gets set to 'iscurrent' = True. The backend API should prevent this from happening as the logic is there to set all other accounts 'iscurrent' attribute to False. This is apparently not working. | [7 empty] | None | [7 empty] | None |  | 0¦1000ug: |  |  | None |  | Not started
Spendsy | SPEN-137 | Going to burnrate page initilally doesn't show burnrate value | Bug | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-25 17:35 |  | 2014-11-27 22:08 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | When the user is logged in with Incomes, Expenses, and Transactions having been already created, they're taken to the Burnrate page. However, the burnrate value in the bottom progress bar shows 0. | [7 empty] | None | [7 empty] | None |  | 0¦1000u8: |  |  | None |  | Not started
Spendsy | SPEN-136 | When the server is restarted, the user's primary income and current account gets unset | Bug | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-25 16:41 |  | 2014-11-25 17:36 | 2014-11-25 17:32 |  |  | API |  | 0 | 1 | [8 empty] | If the server needs to be restarted, or even if the user logs out an back in, the state data is flushed which causes the user's primary income and current account to be unset (as None - the default). This causes the burnrate to show 0 for progress because it doesn't know what the primary income is to calculate the burnrate from. The fix is when a call to get for any entity list for a user (with user_id param) is made, loop through the result and check for the 'isprimary' key and the 'iscurrent' key. If it exists and is True, set this as the primary income and current account respectively. Then when the user logs back in, the primary income and current account are set from the database as they should, and the user sees their burnrate without having to go back in Incomes and update their primary income. | [7 empty] | None | [7 empty] | None |  | 0¦1000u0: |  |  | None |  | Not started
Spendsy | SPEN-135 | SPEN-131 Put note in footer letting users know that ssl is being set up | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-24 13:37 |  | 2014-11-24 15:24 | 2014-11-24 15:24 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000ts: |  |  | None |  | Not started
Spendsy | SPEN-134 | Move all business related expenditures to business account | Task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-24 12:04 |  | 2014-11-24 12:04 |  |  |  | Admin |  | 0 | 1 | [8 empty] | https://clippingmagic.com/ etc... | [7 empty] | None | [7 empty] | None |  | 0¦1000tk: |  |  | None |  | Not started
Spendsy | SPEN-133 | SPEN-132 Create a script that can be used to start app and api servers in the background | Sub-task | To Do | Critical | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-22 10:39 |  | 2014-11-22 10:39 |  |  |  | DevOps |  | 0 | 1 | [8 empty] | Temporary using nohup: http://www.cyberciti.biz/tips/nohup-execute-commands-after-you-exit-from-a-shell-prompt.html Permanent using init.d: http://www.tldp.org/HOWTO/HighQuality-Apps-HOWTO/boot.html http://www.debian-administration.org/article/28/Making_scripts_run_at_boot_time_with_Debian | [7 empty] | None | [7 empty] | None |  | 0¦1000tc: |  |  | None |  | Not started
Spendsy | SPEN-132 | Set up Spendsy web server in Google Cloud ComputeEngine | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-20 23:38 |  | 2014-11-21 11:27 | 2014-11-21 11:27 |  |  | Admin, DevOps |  | 0 | 1 | [5 empty] | SPEN-133 |  |  | https://console.developers.google.com/project/spendsy/compute/instances?hl=en&graph=GCE_CPU To ssh: --- google-cloud-sdk attached --- https://cloud.google.com/compute/docs/gcloud-compute/#install gcloud compute --project "spendsy" ssh --zone "us-central1-a" "spendsy-1" | [7 empty] | None | [7 empty] | None |  | 0¦1000t4: |  |  | None |  | Not started
Spendsy | SPEN-131 | Set up SSL | Task | In Progress | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-20 18:53 |  | 2014-11-21 11:13 |  |  |  | Admin, DevOps, Web Application |  | 0 | 1 | [5 empty] | SPEN-135 |  |  | https://www.digitalocean.com/community/tutorials/how-to-create-an-ssl-certificate-on-nginx-for-ubuntu-14-04 | [7 empty] | None | [7 empty] | None |  | 0¦1000sw: |  |  | None |  | Not started
Spendsy | SPEN-130 | SPEN-34 Create an isspending attribute in Accounts | Sub-task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-19 17:07 |  | 2014-11-19 17:07 |  |  |  | API, Web Application |  | 0 | 1 | [8 empty] | Need to tie isspending to the spending account, so that the burnrate shows only for this account, not for others. | [7 empty] | None | [7 empty] | None |  | 0¦1000so: |  |  | None |  | Not started
Spendsy | SPEN-129 | SPEN-34 As a user, I should see my total net worth on the Accounts page | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-18 17:38 |  | 2014-12-04 17:57 | 2014-12-04 17:57 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000sg: |  |  | None |  | Not started
Spendsy | SPEN-128 | SPEN-34 As a user, I should be able to record funds transfers between accounts | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-18 17:37 |  | 2014-12-04 17:11 | 2014-12-04 17:11 |  |  | API, Web Application |  | 0 | 1 | [6 empty] | SPEN-127 | [9 empty] | None | [7 empty] | None |  | 0¦1000s8: |  |  | None |  | Not started
Spendsy | SPEN-127 | SPEN-34 Transaction activity should change the account balance for the current account | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-18 17:34 |  | 2014-12-10 23:09 | 2014-12-10 23:09 |  |  | API, Web Application |  | 0 | 1 | [6 empty] | SPEN-128 |  | Account balance should be updated when accounts transfers take place, but also when transactions are CRUD'd | [7 empty] | None | [7 empty] | None |  | 0¦1000s0: |  |  | None |  | Not started
Spendsy | SPEN-126 | SPEN-34 Make the selected account the current account | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-18 17:32 |  | 2014-11-22 17:04 | 2014-11-22 17:04 |  |  | API, Web Application |  | 0 | 1 | [8 empty] | When the user selects an account, set that as the current account so when the app loads and the user clicks on accounts or burnrates, or cruds a transaction, the current account is the one affected | [7 empty] | None | [7 empty] | None |  | 0¦1000rs: |  |  | None |  | Not started
Spendsy | SPEN-125 | Selecting an entity for update or deletion picks the first one in the list | Bug | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-17 14:21 |  | 2014-11-17 16:40 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | When choosing an entity to update by clicking the entity's name link, if there are other entities in the list that have the same name, the first one is chosen to display on the update page instead of the one that was actually selected. This makes it impossible to edit or delete other entities since only the first one ever shows up. This is happening because the name of the entity is being resolved to it's id in the backend (web/app/models.py:32). For updates and deletions, need to map the name to the id in the template, not the backend since the template is the only place where we can be sure we have the right object. This will require the id be in the url. This is acceptable for update and delete operations. | [7 empty] | None | [7 empty] | None |  | 0¦1000rk: |  |  | None |  | Not started
Spendsy | SPEN-124 | Create a Product Requirements Document | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-14 13:24 |  | 2014-11-30 10:11 |  |  |  | Admin, Marketing |  | 0 | 1 | [8 empty] | Alejandra Carlos created a Product Requirements Document. https://drive.google.com/a/spendsy.me/#my-drive | [7 empty] | None | [7 empty] | None |  | 0¦1000rc: |  |  | None |  | Not started
Spendsy | SPEN-123 | Div overflow on app pages causing gap in right side of header and footer | Bug | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-13 08:22 |  | 2014-11-13 08:22 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000r4: |  |  | None |  | Not started
Spendsy | SPEN-122 | Get user feedback | Epic | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-08 11:45 |  | 2014-11-08 11:45 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None |  | ghx-label-3 |  | Get user feedback | To Do |  |  | None |  | 0¦1000qw: |  |  | None |  | Not started
Spendsy | SPEN-121 | Guide user through Spendsy | Epic | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-08 11:45 |  | 2014-11-08 11:45 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None |  | ghx-label-1 |  | Guide user | To Do |  |  | None |  | 0¦1000qo: |  |  | None |  | Not started
Spendsy | SPEN-120 | Prevent XSS attacks | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-07 16:30 |  | 2014-11-07 16:30 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | http://flask.pocoo.org/docs/0.10/security/ | [7 empty] | None | [7 empty] | None |  | 0¦1000qg: |  |  | None |  | Not started
Spendsy | SPEN-119 | Use jinja2 to move duplicate html code into layout file(s) | Bug | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-07 00:07 |  | 2014-11-30 16:52 |  |  |  | Web Application |  | 0 | 1 | [6 empty] | SPEN-140 | [9 empty] | None | [7 empty] | None |  | 0¦1000q8: |  |  | None |  | Not started
Spendsy | SPEN-118 | Transactions not being sorted by date | Bug | In Review | Minor | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-04 13:58 |  | 2014-11-24 13:29 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000q0: |  |  | None |  | Not started
Spendsy | SPEN-117 | Get trust verification seals to put in footer for all pages | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-04 13:41 |  | 2014-11-04 13:41 |  |  |  | Marketing, Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000ps: |  |  | None |  | Not started
Spendsy | SPEN-116 | Turn off Google Analytics for dev env and personal use of Spendsy | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-03 15:27 |  | 2014-11-03 15:46 | [5 empty] | 0 | 1 | [8 empty] | 1) Set environment variable on dev machine(s) => echo 'export SPENDSY_DEV="True"' >> ~/.bash_profile && source ~/.bash_profile 2) Check for the environment variable in utils.App for every page that has google analytics tracking code and pass in a context variable that tells whether or not the server is a dev or prod server. 3) Wrap the google analytics javascript code with an if statement that checks whether the SPENDSY_DEV env variable is set to True or not. | [7 empty] | None | [7 empty] | None |  | 0¦1000pk: |  |  | None |  | Not started
Spendsy | SPEN-115 | Find quotes from various financial gurus to put up on the site | Task | In Progress | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-11-01 01:40 |  | 2014-11-01 01:48 |  |  |  | Marketing, Web Application |  | 0 | 1 | [6 empty] | SPEN-105 |  | Get quotes from: Napoleon Hill Dave Ramsey Earl Nightingale Joel Osteen Suze Orman Warren Buffet Holton Buggs Shane Morand http://www.brainyquote.com/ https://www.goodreads.com/quotes | [7 empty] | None | [7 empty] | None |  | 0¦1000pc: |  |  | None |  | Not started
Spendsy | SPEN-114 | SPEN-89 Script the pulling of links from cj.com to update ads.py | Sub-task | In Progress | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-30 17:14 |  | 2014-11-07 18:24 |  |  |  | DevOps, Marketing, Web Application |  | 0 | 1 | [8 empty] | • Use the CJ api to get links from cj.com: http://cjsupport.custhelp.com/app/answers/detail/a_id/1552/kw/links%20api ¦ http://cjsupport.custhelp.com/app/answers/detail/a_id/1552. Example call: https://linksearch.api.cj.com/v2/link-search?website-id=7683137&advertiser-ids=joined headers: {'authorization': '00bde8c3876db74e4afc09c9df0529653cf65bc299daf692a2a129acf9bae50782bed7a56ddcb4dbf9470a199bced375c8923c4b3746d245b828661b9787116c41/0083477ca309fd456a2080c3c41fd555dea68f181f337670376c215b29e7409bc75b553bb9bdf404babbcc70b221637606a4785b98c89abc60b540c928e99d4de1'} • Scrub the csv file of any unusable links • Format the data to fit into the appropriate dictionary in ads.py • Create a cron job to pull the links daily and run the task to update the ads | [7 empty] | None | [7 empty] | None |  | 0¦1000p4: |  |  | None |  | Not started
Spendsy | SPEN-113 | Make create pages for all functional areas | Task | In Progress | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-30 16:10 |  | 2014-11-04 09:21 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | Each functional area that accepts input or creates a new entity should have a seperate "create" page like they have "update" and "delete" pages. The index page should only show the table with the entered data and any supporting information. | [7 empty] | None | [7 empty] | None |  | 0¦1000ow: |  |  | None |  | Not started
Spendsy | SPEN-112 | Collect statistics on budgeting and finance to put on the site | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-30 16:00 |  | 2014-11-01 01:47 |  |  |  | Marketing, Web Application |  | 0 | 1 | [6 empty] | SPEN-105 |  | http://www.businessinsider.com/a-dozen-shocking-personal-finance-statistics-2011-5 | [7 empty] | None | [7 empty] | None |  | 0¦1000oo: |  |  | None |  | Not started
Spendsy | SPEN-111 | Replace 3D nav link tabs on app pages | Improvement | Done | Minor | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-30 13:19 |  | 2014-10-30 15:16 | 2014-10-30 15:16 |  |  | Web Application |  | 0 | 1 | [8 empty] | The nav links as 3D tabs look ugly. Need something better. Need to get rid of the spaces between the tabs. That's what I was initially trying for, but it didn't want to work. | [7 empty] | None | [7 empty] | None |  | 0¦1000og: |  |  | None |  | Not started
Spendsy | SPEN-110 | Replace old html templates with new ones | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-30 09:08 |  | 2014-10-30 12:50 | 2014-10-30 12:50 |  |  | Web Application |  | 0 | 1 | [8 empty] | Some templates are named "new_<template_name>" to replace old templates while refactoring the look and feel of the app. • Need to rename the old templates without the "new_" prefix so that these become the old templates and create room for even newer templates that will have the "new_" prefix. • Arrange functional areas into folders of that area name, e.g. incomes.html => incomes/index.html, delete_income.html => incomes/delete.html, etc. • Create temporary conditional statements in the views.py file to call on any new templates that exist, otherwise use old templates (without the "new_" prefix). | [7 empty] | None | [7 empty] | None |  | 0¦1000o8: |  |  | None |  | Not started
Spendsy | SPEN-109 | Get icons for home page | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-30 00:30 |  | 2014-10-30 10:21 | 2014-10-30 10:21 |  |  | Marketing, Web Application |  | 0 | 1 | [8 empty] | https://www.iconfinder.com/search/?q=income; creds: cgjonesdev/<main_secure_password> http://www.istockphoto.com/vector/finance-amp-investment-icon-set-concise-series-27371052?st=7b4b891 | [7 empty] | None | [7 empty] | None |  | 0¦1000o0: |  |  | None |  | Not started
Spendsy | SPEN-108 | Change logo to real image of a silver coin | Task | To Do | Critical | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-29 19:27 |  | 2014-10-29 19:27 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000ns: |  |  | None |  | Not started
Spendsy | SPEN-107 | Learn how to use ofx to connect to bank accounts to get transactions | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-29 19:26 |  | 2014-10-29 19:26 |  |  |  | Research |  | 0 | 1 | [8 empty] | http://www.ofx.net/DeveloperSolutions.aspx http://wiki.gnucash.org/wiki/OFX_Direct_Connect_Bank_Settings | [7 empty] | None | [7 empty] | None |  | 0¦1000nk: |  |  | None |  | Not started
Spendsy | SPEN-106 | Income is set to false when updated if check box is not checked | Bug | To Do | Critical | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-29 19:24 |  | 2014-10-29 19:24 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000nc: |  |  | None |  | Not started
Spendsy | SPEN-105 | As a user, I should see text content on the app pages | Epic | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-28 20:34 |  | 2014-11-01 01:47 |  |  |  | Marketing, Web Application |  | 0 | 1 | [6 empty] | SPEN-115, SPEN-112 | [9 empty] | None | [7 empty] | None |  | 0¦1000n4: |  |  | None |  | Not started
Spendsy | SPEN-104 | Create a Marketing Requirements Document | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-28 15:50 |  | 2014-12-04 17:16 |  |  |  | Admin, Marketing |  | 0 | 1 | [8 empty] | Alejandra Carlos created an MRD. https://drive.google.com/a/spendsy.me/#my-drive | [7 empty] | None | [7 empty] | None |  | 0¦1000mw: |  |  | None |  | Not started
Spendsy | SPEN-103 | As a spendsy administrator, I need an admin panel | Story | In Progress | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-28 14:46 |  | 2014-10-31 07:50 |  |  |  | Admin, Web Application |  | 0 | 1 | [8 empty] | Need to create an admin panel so I can see a list of users with new users for each of the last seven days highlighted in a different color. The admin panel should be behind a seperate admin login. | [7 empty] | None | [7 empty] | None |  | 0¦1000mo: |  |  | None |  | Not started
Spendsy | SPEN-102 | Create directory for ads | Task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-28 10:26 |  | 2014-11-27 11:10 |  |  |  | Revenue, Web Application |  | 0 | 1 | [8 empty] | Need a place to store ad info to keep ads organized. The python files will serve to keep ads organized by advertiser, size, and type. The App class in utils will call on these files to serve ad content randomly using python's random number generator. | [7 empty] | None | [7 empty] | None |  | 0¦1000mg: |  |  | None |  | Not started
Spendsy | SPEN-101 | Set up Spendsy business bank account | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-27 12:00 |  | 2014-10-28 20:20 | 2014-10-28 15:57 |  |  | Admin |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000m8: |  |  | None |  | Not started
Spendsy | SPEN-100 | Set up Spendsy business email in gmail | Task | In Progress | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-27 11:54 |  | 2014-10-27 13:55 |  |  |  | Admin, DevOps |  | 0 | 1 | [8 empty] | Admin console: https://admin.google.com/spendsy.me/AdminHome?firsttime=pre#Home: | [7 empty] | None | [7 empty] | None |  | 0¦1000m0: |  |  | None |  | Not started
Spendsy | SPEN-99 | Set up Commission Junction account to get ads to put on Spendsy site | Task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-27 11:42 |  | 2014-10-27 12:31 |  |  |  | Marketing |  | 0 | 1 | [8 empty] | http://www.cj.com/ Login: cgjonesdev@gmail.com/%Qi5qRRf | [7 empty] | None | [7 empty] | None |  | 0¦1000ls: |  |  | None |  | Not started
Spendsy | SPEN-98 | Set up Google Adwords advertising for Spendsy | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-27 11:40 |  | 2014-10-27 11:40 | 2014-10-27 11:40 |  |  | Marketing |  | 0 | 1 | [8 empty] | Login: cgjonesdev@gmail.com | [7 empty] | None | [7 empty] | None |  | 0¦1000lk: |  |  | None |  | Not started
Spendsy | SPEN-97 | State data is persisting between users | Bug | Done | Critical | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 21:19 |  | 2014-10-25 22:15 | 2014-10-25 22:15 |  |  | Web Application |  | 0 | 1 | [8 empty] | When a new user is created, the idea is that they have never done anything in the app before, so it would be impossible for them to have budget data or a burnrate or any transactions, etc. Currently, after a new user is created and another user was just logged in, they are seeing the old user's information. Solution: Clear all state data up login just before instantiating it to make sure none of the previous user's data is stale and persisting to the new user's view. | [7 empty] | None | [7 empty] | None |  | 0¦1000lc: |  |  | None |  | Not started
Spendsy | SPEN-96 | Make banner ads responsive | Improvement | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 21:10 |  | 2014-10-25 21:10 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | http://matthewjamestaylor.com/blog/responsive-banner-ads | [7 empty] | None | [7 empty] | None |  | 0¦1000l4: |  |  | None |  | Not started
Spendsy | SPEN-95 | As a user, if I already have an account, I should not be able to sign up again | Bug | To Do | Critical | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 21:04 |  | 2014-11-12 15:42 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | The user can now go straight to the signup page via the new signup link. Before, the idea was that the user would enter login credentials. If they didn't exist, the user was taken to the signup page. Their login creds were then bundled into the json sent to the server where they're vaidated to see if the account exists or not by verifying the password hash. Now that they can go straight to the signup page, it's possible to create an accout without any validation. Once the user fills out the signup form data, they need to be redirected to the login page where they enter login credentials which will be validated to see if their account already exists. Since this step validates their account using a hash, we can be completely confident that their account either exists or it doesn't. If it does (maybe they forgot they already had an account), their signup form data is discarded and they are logged in, i.e. from this point, the normal login validation takes over. | [7 empty] | None | [7 empty] | None |  | 0¦1000kw: |  |  | None |  | Not started
Spendsy | SPEN-94 | Swap Transactions and Budget nav links | Improvement | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 20:40 |  | 2014-10-25 20:40 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | Budget goes more with incomes and expenses and transactions goes more with burnrate. Transactions and budget should be swapped. | [7 empty] | None | [7 empty] | None |  | 0¦1000ko: |  |  | None |  | Not started
Spendsy | SPEN-93 | 2Modern ad overlaps spent info on burnrate page | Bug | To Do | Critical | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 18:35 |  | 2014-10-25 18:35 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000kg: |  |  | None |  | Not started
Spendsy | SPEN-92 | SPEN-90 Update the pricing page with info that tells what the user can expect to pay for using the site | Sub-task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 18:06 |  | 2014-10-25 22:41 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | Explain to the user that for now, use of the app is free, and that there are ads, but down the road, there will be a choice of whether or not to opt out of ads for a monthly fee. Also, for users who would like to save money, there will also be the option to be charge per api call, rather than a flat fee. | [7 empty] | None | [7 empty] | None |  | 0¦1000k8: |  |  | None |  | Not started
Spendsy | SPEN-91 | SPEN-90 Update the features page with info that tells about what the site has to offer | Sub-task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 18:06 |  | 2014-10-25 22:37 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | List of features (what does the app do?): | [7 empty] | None | [7 empty] | None |  | 0¦1000k0: |  |  | None |  | Not started
Spendsy | SPEN-90 | Need pages to market the site and explain what it's about | Story | To Do | Critical | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 18:02 |  | 2014-10-25 18:02 |  |  |  | Web Application |  | 0 | 1 | [5 empty] | SPEN-91, SPEN-92 | [10 empty] | None | [7 empty] | None |  | 0¦1000js: |  |  | None |  | Not started
Spendsy | SPEN-89 | As a company, I can generate revenue through placing ads on the site | Epic | In Progress | Critical | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 17:35 |  | 2014-10-30 17:00 |  |  |  | Web Application |  | 0 | 1 | [5 empty] | SPEN-114 |  |  | https://members.cj.com/member/publisher/home.do | [7 empty] | None | [7 empty] | None |  | 0¦1000jk: |  |  | None |  | Not started
Spendsy | SPEN-88 | User is able to sign up with no information | Bug | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 16:26 |  | 2014-10-25 16:29 | 2014-10-25 16:29 |  |  |  |  | 0 | 1 | [8 empty] | On the signup page, the user can click the signup button with no information in the fields and go to the incomes page. At least the First name and Last name fields should be required. | [7 empty] | None | [7 empty] | None |  | 0¦1000jc: |  |  | None |  | Not started
Spendsy | SPEN-87 | Need to add option on home page for user to create an account | Improvement | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 14:52 |  | 2014-10-25 16:08 | 2014-10-25 16:08 |  |  | Web Application |  | 0 | 1 | [8 empty] | User needs to be informed on the home page that they can create an account as well as login. | [7 empty] | None | [7 empty] | None |  | 0¦1000j4: |  |  | None |  | Not started
Spendsy | SPEN-86 | Set up google analytics for spensy.me | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 14:23 |  | 2014-10-25 14:33 | 2014-10-25 14:33 |  |  | Admin, Web Application |  | 0 | 1 | [8 empty] | https://www.google.com/intl/en/analytics/ | [7 empty] | None | [7 empty] | None |  | 0¦1000iw: |  |  | None |  | Not started
Spendsy | SPEN-85 | Expenses table heading says "Pay date" instead of "Due date" | Bug | Done | Minor | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 12:35 |  | 2014-10-25 12:41 | 2014-10-25 12:41 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000io: |  |  | None |  | Not started
Spendsy | SPEN-84 | Table heading and data font is too large | Improvement | Done | Minor | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 12:09 |  | 2014-10-25 12:14 | 2014-10-25 12:14 |  |  | Web Application |  | 0 | 1 | [8 empty] | Reduce table heading and data font size to 1.7em and 1.65em respectively. | [7 empty] | None | [7 empty] | None |  | 0¦1000ig: |  |  | None |  | Not started
Spendsy | SPEN-83 | Transactions doesn't have a selector for credit/debit | Bug | Done | Critical | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 11:36 |  | 2014-10-25 11:53 | 2014-10-25 11:48 |  |  | Web Application |  | 0 | 1 | [8 empty] | After redesigning the web application, I forgot to include the transaction type selector so the user can say whether the transaction is a credit or debit. | [7 empty] | None | [7 empty] | None |  | 0¦1000i8: |  |  | None |  | Not started
Spendsy | SPEN-82 | As a user, I should see my transactions sorted in date order | Story | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 10:42 |  | 2014-10-25 11:32 | 2014-10-25 11:32 |  |  | API, Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000i0: |  |  | None |  | Not started
Spendsy | SPEN-81 | New user has to log out and back in again after creating initial incomes and expenses | Bug | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 00:39 |  | 2014-10-31 22:34 | 2014-10-31 22:24 |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000hs: |  |  | None |  | Not started
Spendsy | SPEN-80 | Transactions table shows "Cycle" and "Is Primary" as row headings | Bug | To Do | Minor | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 00:38 |  | 2014-10-25 00:38 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | Row headers should be "Memo" and "Confirmation Number" instead of "Cycle" and "Is Primary". | [7 empty] | None | [7 empty] | None |  | 0¦1000hk: |  |  | None |  | Not started
Spendsy | SPEN-79 | Transaction doesn't show in Burnrate if the date is older than today | Bug | Done | Critical | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-25 00:34 |  | 2014-10-25 10:13 | 2014-10-25 10:13 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000hc: |  |  | None |  | Not started
Spendsy | SPEN-78 | Budget title says Burnrate | Bug | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-24 23:58 |  | 2014-10-25 | 2014-10-24 23:59 |  |  | Web Application |  | 0 | 1 | [8 empty] | Change Budget title to {{ user.firstname }}'s Budget instead of {{ user.firstname }}'s Burnrate. | [7 empty] | None | [7 empty] | None |  | 0¦1000h4: |  |  | None |  | Not started
Spendsy | SPEN-77 | Make hyperlink in tables for Entities obvious | Improvement | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-24 23:40 |  | 2014-10-25 00:13 | 2014-10-25 00:12 |  |  | Web Application |  | 0 | 1 | [8 empty] | User should be able to tell that the items (name for all, website for expenses) can be clicked on to see a detailed page for that entity by making them underlined. | [7 empty] | None | [7 empty] | None |  | 0¦1000gw: |  |  | None |  | Not started
Spendsy | SPEN-76 | Can't enter Incomes, Expenses, or Transactions in browsers that don't support date input field | Bug | Done | Critical | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-24 23:36 |  | 2014-10-28 01:11 | 2014-10-28 01:11 |  |  |  |  | 0 | 1 | [8 empty] | Only Chrome provides a calendar type date chooser. The form data is sent to the api as Chrome provides it, but there is no error correction for how a user enters a date in other browsers. | [7 empty] | None | [7 empty] | None |  | 0¦1000go: |  |  | None |  | Not started
Spendsy | SPEN-75 | When adding an expense, cycle was automatically set to week | Bug | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-24 23:28 |  | 2014-10-24 23:30 | 2014-10-24 23:30 |  |  | Web Application |  | 0 | 1 | [8 empty] | Even though the selector said "month(s)" the value was set to "week" because when creating this template, it was copied over from incomes. | [7 empty] | None | [7 empty] | None |  | 0¦1000gg: |  |  | None |  | Not started
Spendsy | SPEN-74 | Expenses website is not a link | Bug | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-24 23:01 |  | 2014-10-24 23:25 | 2014-10-24 23:25 |  |  | Web Application |  | 0 | 1 | [8 empty] | Make the website part of Expenses a hyperlink to the site | [7 empty] | None | [7 empty] | None |  | 0¦1000g8: |  |  | None |  | Not started
Spendsy | SPEN-73 | Switch from budgetwise db to spendsy | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-24 22:44 |  | 2014-10-24 23:01 | 2014-10-24 23:01 |  |  | API, MongoDB |  | 0 | 1 | [8 empty] | Rename database from budgetwise to spendsy. This will effectively cause the database to start from scratch with no users or other info. Trying to migrate changes over has proven to be a nightmare. May be best to just start fresh. | [7 empty] | None | [7 empty] | None |  | 0¦1000g0: |  |  | None |  | Not started
Spendsy | SPEN-72 | SPEN-25 Restyle templates using main style.css file where possible | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-23 14:05 |  | 2014-10-24 21:22 | 2014-10-24 21:22 |  |  | Web Application |  | 0 | 1 | [8 empty] | The reason for "where possible" in the title is that in some cases (such as burnrate.html - where there are progress bars whose values need to be set by context variables). | [7 empty] | None | [7 empty] | None |  | 0¦1000fs: |  |  | None |  | Not started
Spendsy | SPEN-71 | Move logo in front of Spendsy text | Improvement | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-23 12:42 |  | 2014-10-23 13:49 | 2014-10-23 13:49 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000fk: |  |  | None |  | Not started
Spendsy | SPEN-70 | Change tab titles to be more consistent | Improvement | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-23 09:46 |  | 2014-10-23 12:43 | 2014-10-23 12:42 |  |  | Web Application |  | 0 | 1 | [8 empty] | Currently, the tab titles are mixed. For Incomes, Expenses, and Transactions, it just shows the name of the currently set income, expense, or transaction - which makes no sense for a list of items (how do you know which one should be displayed?). Budget and Burnrate burnrate tab titles are correct. Settings says the users first and last names. All tab titles should be composed of the user's first name followed by an 's and the name of the entity or functional area (ex. John's Incomes). Edit and delete pages should have Edit or Delete, then the name of the specific entity being edited or deleted. | [7 empty] | None | [7 empty] | None |  | 0¦1000fc: |  |  | None |  | Not started
Spendsy | SPEN-69 | Burnrate shows red on progress bar for exactly 25% | Bug | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-22 23:05 |  | 2014-10-23 13:47 | 2014-10-23 13:44 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000f4: |  |  | None |  | Not started
Spendsy | SPEN-68 | As as user, I should see a 404 page if a resource is not found or something goes wrong | Story | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-09 17:16 |  | 2014-10-09 17:16 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000ew: |  |  | None |  | Not started
Spendsy | SPEN-67 | Change budgetwise_api virtualenv name to spendsy_api | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-03 07:27 |  | 2014-10-23 14:00 | 2014-10-23 13:53 |  |  | API |  | 0 | 1 | [6 empty] | SPEN-38 |  | - Use pip freeze to save dependencies to a requirements.txt file (workon budgetwise_api && pip freeze > requirements.txt) - Create new virtualenv called "spendsy_api" and run the virtual env (mkvirtualenv spendsy_api && workon spendsy_api) - Install dependencies (pip install -r requirements.txt) - Push requirements.txt file to remote repo | [7 empty] | None | [7 empty] | None |  | 0¦1000eo: |  |  | None |  | Not started
Spendsy | SPEN-66 | Change budgetwise_app virtualenv name to spendsy | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-03 07:25 |  | 2014-10-23 14:00 | 2014-10-23 13:44 |  |  | Web Application |  | 0 | 1 | [6 empty] | SPEN-38 |  | - Use pip freeze to save dependencies to a requirements.txt file (workon budgetwise_app && pip freeze > requirements.txt) - Create new virtualenv called "spendsy" and run the virtual env (mkvirtualenv spendsy && workon spendsy) - Install dependencies (pip install -r requirements.txt) - Push new requirements.txt file to remote repo | [7 empty] | None | [7 empty] | None |  | 0¦1000eg: |  |  | None |  | Not started
Spendsy | SPEN-65 | Read "RESTful Web APIs" | Task | In Progress | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-10-01 20:20 |  | 2014-10-23 13:45 |  |  |  | Study |  | 0 | 1 | [8 empty] | http://shop.oreilly.com/product/0636920028468.do | [7 empty] | None | [7 empty] | None |  | 0¦1000e8: |  |  | None |  | Not started
Spendsy | SPEN-64 | As a user, I my bills pool should be built up before starting a savings pool | Bug | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-14 15:50 |  | 2014-09-14 16:16 |  |  |  | API |  | 0 | 1 | [8 empty] | Calculate the savings amount only after the bills pool has been built up to the point that the user has enough to pay any bills at any time. One way to accomplish this is to not save any money until the bills pool is completely built up. Another way to is calculate a ramp-up amount for each paycheck until the bills pool is complete so the user doesn't think they can't save any money at all. Calculations: total bills pool amount = total monthly expense amount (this should work as a proper padding amount since most bills are due monthly) set aside for bills in account = account balance - core.Budget.spending partial savings amount = total bills pool amount - set aside for bills in account bills pool percentage = set aside for bills in account / total bills pool amount ramped up partial savings amount = bills pool percentage * core.Budget.savings | [7 empty] | None | [7 empty] | None |  | 0¦1000e0: |  |  | None |  | Not started
Spendsy | SPEN-63 | Plan application flow | Epic | To Do | Critical | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-12 18:45 |  | 2014-09-12 18:45 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | Create a flowchart that describes the layout and flow of the application. Every software program provides functionality, but to do so, it must tell a "story". The flowchart should describe the story the app is trying to tell from start to finish and how that story maps to what the app is trying to accomplish. | [7 empty] | None |  | ghx-label-1 |  | Application flow | To Do |  |  | None |  | 0¦1000ds: |  |  | None |  | Not started
Spendsy | SPEN-62 | Refactor user authentication from the Web Applicaiton to the API | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-11 09:13 |  | 2014-10-23 13:56 | 2014-10-23 13:53 |  |  |  |  | 0 | 1 | [8 empty] | Research authentication schemes and find out what the most secure type is. Currently, I think we're just using a custom implementation of Basic Authentication. http://tools.ietf.org/html/rfc2617 http://msdn.microsoft.com/en-us/library/ms789031(v=vs.110).aspx http://www.w3.org/Protocols/HTTP/1.0/spec.html#AA | [7 empty] | None | [7 empty] | None |  | 0¦1000dk: |  |  | None |  | Not started
Spendsy | SPEN-61 | SPEN-59 Refactor Web Application code | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-11 08:35 |  | 2014-10-22 22:49 | 2014-10-22 22:48 |  |  |  |  | 0 | 1 | [8 empty] | - Create models.py and add classes that describe the objects and their contents - Create controllers.py, move the logic of what's done to the objects there from app.py - Create views.py and use it to display templates based on any changes made in the controllers - Create urls.py and move all url routing there Use class based views as described here: http://flask.pocoo.org/docs/0.10/views/ | [7 empty] | None | [7 empty] | None |  | 0¦1000dc: |  |  | None |  | Not started
Spendsy | SPEN-60 | SPEN-59 Refactor API code | Sub-task | Done | Critical | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-11 08:34 |  | 2014-10-09 22:22 | 2014-09-13 18:34 |  |  |  |  | 0 | 1 | [8 empty] | - Rename core.py to models.py - Recreate core.py and move utility classes there - Create controllers.py to handle logic performed on models data - Rename resources.py to views.py and move argument parser and logic in here to controllers.py. This file should only be used to pass logic from controllers to requesting url endpoints. - Create urls.py and move the url routers there ---------------------------------------------------------------------------------------------------- - Pull in updated code from https://spendsy.atlassian.net/browse/SPEN-61 - Implement python magic methods (__methodname__) to make instance objects more versatile | [7 empty] | None | [7 empty] | None |  | 0¦1000d4: |  |  | None |  | Not started
Spendsy | SPEN-59 | Refactor API and Web Application code to use MVC-style architecture | Task | Done | Critical | Done | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-11 08:20 |  | 2014-10-22 22:52 | 2014-10-22 22:52 |  |  | API, Web Application |  | 0 | 1 | [5 empty] | SPEN-60, SPEN-61 |  |  | This will allow the application to scale out better and make it easier to add new functionaility | [7 empty] | None | [7 empty] | None |  | 0¦1000cw: |  |  | None |  | Not started
Spendsy | SPEN-58 | Read "CSS3 Pushing The Limits" | Task | In Progress | Minor | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-04 20:07 |  | 2014-09-11 23:43 |  |  |  | Study |  | 0 | 1 | [8 empty] | http://www.wiley.com/WileyCDA/WileyTitle/productCd-1118652630.html | [7 empty] | None | [7 empty] | None |  | 0¦1000co: |  |  | None |  | Not started
Spendsy | SPEN-57 | Incomes and Expenses cannot be updated or deleted | Bug | Done | Blocker | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-02 18:14 |  | 2014-09-03 01:05 | 2014-09-03 01:05 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000cg: |  |  | None |  | Not started
Spendsy | SPEN-56 | Move password hash cookie to encrypted session | Task | Done | Critical | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-01 14:18 |  | 2014-10-23 13:51 | 2014-10-23 13:51 |  |  | Web Application |  | 0 | 1 | [8 empty] | Currently, the user's hashed password is being stored in the browser's cookies so if they are idle for more than 15 minues, they will need to log back in. This hashed password needs to not be stored as a cookie even though it's hashed. Need to store this as encrypted session data. This will involve rewriting the code in each view function that stores the cookie in the browser to store it as a session as well as the fuction in AppData that checks the cookie's value to look in the session data instead. | [7 empty] | None | [7 empty] | None |  | 0¦1000c8: |  |  | None |  | Not started
Spendsy | SPEN-55 | Autofocus name text box for Login, Signup, Incomes, Expenses, and Transactions pages | Task | Done | Trivial | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-01 13:41 |  | 2014-09-03 09:24 | 2014-09-03 09:24 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000c0: |  |  | None |  | Not started
Spendsy | SPEN-54 | Login redirects to /summary when creating a new user | Bug | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-09-01 11:08 |  | 2014-09-01 13:38 | 2014-09-01 13:38 |  |  | Web Application |  | 0 | 1 | [8 empty] | When a new user is being created, instead of redirecting to /summary, they should be redirected to /signup since they don't have an account yet. When the request method in signup is GET, the signup.html page should show. When the method is POST, the new user should be created, then the app should redirect to /login so they can log into the app. | [7 empty] | None | [7 empty] | None |  | 0¦1000bs: |  |  | None |  | Not started
Spendsy | SPEN-53 | User is taken back to the home page before the auth cookie times out | Bug | To Do | Critical | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-29 23:52 |  | 2014-09-02 18:18 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | Occasionally (not sure yet when this is happening, although it seems to be when transitioning from one page to another), the user has to log back in immediately instead of having the full 15 minutes, which should get updated with every API call, before they have to log back in. | [7 empty] | None | [7 empty] | None |  | 0¦1000bk: |  |  | None |  | Not started
Spendsy | SPEN-52 | Add versioning to API urls | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-29 23:50 |  | 2014-08-29 23:50 | [5 empty] | 0 | 1 | [8 empty] | For example: "/api/v1/users" | [7 empty] | None | [7 empty] | None |  | 0¦1000bc: |  |  | None |  | Not started
Spendsy | SPEN-51 | As a user I should have my income and expense dates incremented automatically | Story | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-29 23:48 |  | 2014-08-29 23:48 |  |  |  | API, Web Application |  | 0 | 1 | [8 empty] | Currently, the user has to manually increment their incomes and expenses to the next date once the end date for the cycle has passed. The system should automatically increment the cycle by the object's .cycle_in_days() value. In the case of incomes, the system should prompt the user if the pay date has passed, to confirm the amount set previously, or enter a new amount. In the case of expenses, a Due page or modal should show a list of upcoming expenses due and prompt the user as to whether or not to mark the item(s) as paid. If so, the item's date value should be incremented, and the amount, memo, and confirmation values should be added to the transactions list. | [7 empty] | None | [7 empty] | None |  | 0¦1000b4: |  |  | None |  | Not started
Spendsy | SPEN-50 | Take ids out of urls | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-29 23:15 |  | 2014-10-23 13:56 | 2014-10-23 13:54 |  |  | Web Application |  | 0 | 1 | [8 empty] | Remove the ids from the urls in the web application and replace them with the name of the resource being requested. Example: "caryjones/incomes/53cad762e9b88bc5487e2998/update" should be "/caryjones/incomes/keyingredient/update" The id's can be passed from the template using the input type "hidden". | [7 empty] | None | [7 empty] | None |  | 0¦1000aw: |  |  | None |  | Not started
Spendsy | SPEN-49 | Login page should inform the user that they can create a new account | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-29 20:08 |  | 2014-08-29 20:12 | 2014-08-29 20:12 |  |  | Web Application |  | 0 | 1 | [8 empty] | Currently, the login page apppears to assume that you have an account already. In reality, you can create an account by entering a username and password. If your credentials are not in the database already, you are taken to a signup page, but there is nothing on the main login page that says a user and create an account if they don't already have one. | [7 empty] | None | [7 empty] | None |  | 0¦1000ao: |  |  | None |  | Not started
Spendsy | SPEN-48 | Failed login message not showing correctly | Bug | Done | Minor | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-29 19:59 |  | 2014-08-29 20:03 | 2014-08-29 20:03 |  |  | Web Application |  | 0 | 1 | [8 empty] | When the user logs in with the wrong password, the message had no space between the period of the first sentence and the first word of the second sentence which also caused the template not to recognize the string and show the message in black instead of red. | [7 empty] | None | [7 empty] | None |  | 0¦1000ag: |  |  | None |  | Not started
Spendsy | SPEN-47 | SPEN-46 Refactor Burnrate class in core.py as Statistics | Sub-task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-29 19:41 |  | 2014-08-29 19:41 |  |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦1000a8: |  |  | None |  | Not started
Spendsy | SPEN-46 | As a user I should be able to see statistics | Story | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-29 19:39 |  | 2014-08-29 19:39 |  |  |  | API, Web Application |  | 0 | 1 | [5 empty] | SPEN-47 | [10 empty] | None | [7 empty] | None |  | 0¦1000a0: |  |  | None |  | Not started
Spendsy | SPEN-45 | Require api key to connect to the API | Task | Done | Critical | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-29 13:04 |  | 2014-10-23 13:52 | 2014-10-23 13:52 |  |  | API |  | 0 | 1 | [8 empty] | I think the way to do this is to set up an api key and have hard-coded in the web application. Anyone else (or any other consumers) would have to register for the key. https://coderwall.com/p/4qickw | [7 empty] | None | [7 empty] | None |  | 0¦10009s: |  |  | None |  | Not started
Spendsy | SPEN-44 | As a user I should be able to enter items into a wishlist | Story | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-28 17:48 |  | 2014-08-28 17:53 |  |  |  | API, Web Application |  | 0 | 1 | [8 empty] | The wishlist will allow the user to enter things they want to purchase in the near future. It will record data about the items such as name, amount, and date desired, and calculate the affordability of each item including when they would be able to make the purchase given their current income and expense load. This has been implemented as an experiment using inline javascript and can be referenced here: https://github.com/Spendsy/documents/blob/master/experiments/wishlist/index.html | [7 empty] | None | [7 empty] | None |  | 0¦10009k: |  |  | None |  | Not started
Spendsy | SPEN-43 | Refactor Burnrate class | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-28 17:30 |  | 2014-10-23 13:56 | 2014-10-23 13:54 |  |  | API |  | 0 | 1 | [8 empty] | The Burnrate class works, but the code needs to be broken out more into methods that intuitively describe the different functional areas of the class. At a high level, some of those areas would be 1) getting time attributes and 2) getting monetary attributes. The burnrate experiment code that was implemented as a console app in python can be referenced here: https://github.com/Spendsy/documents/blob/master/experiments/burn_rate.py | [7 empty] | None | [7 empty] | None |  | 0¦10009c: |  |  | None |  | Not started
Spendsy | SPEN-42 | As a user I should be able to sort and filter my transactions | Story | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-28 17:20 |  | 2014-08-28 17:20 |  |  |  | API, Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦100094: |  |  | None |  | Not started
Spendsy | SPEN-41 | As a user I should see transactions sorted by date | Story | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-20 17:29 |  | 2014-08-28 17:21 |  |  |  | Web Application |  | 0 | 1 | [8 empty] | # example.py # # Sort a list of a dicts on a common key rows = [ {'fname': 'Brian', 'lname': 'Jones', 'uid': 1003}, {'fname': 'David', 'lname': 'Beazley', 'uid': 1002}, {'fname': 'John', 'lname': 'Cleese', 'uid': 1001}, {'fname': 'Big', 'lname': 'Jones', 'uid': 1004} ] from operator import itemgetter rows_by_fname = sorted(rows, key=itemgetter('fname')) rows_by_uid = sorted(rows, key=itemgetter('uid')) from pprint import pprint print("Sorted by fname:") pprint(rows_by_fname) print("Sorted by uid:") pprint(rows_by_uid) rows_by_lfname = sorted(rows, key=itemgetter('lname','fname')) print("Sorted by lname,fname:") pprint(rows_by_lfname) | [7 empty] | None | [7 empty] | None |  | 0¦10008w: |  |  | None |  | Not started
Spendsy | SPEN-40 | Research csrf token for flask | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-19 16:37 |  | 2014-08-19 16:37 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10008o: |  |  | None |  | Not started
Spendsy | SPEN-39 | Set up devs@spendsy.me correctly | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-19 16:08 |  | 2014-08-19 16:08 |  |  |  | DevOps |  | 0 | 1 | [8 empty] | Currently emails to this address bouce: Delivery to the following recipient failed permanently: devs@spendsy.me Technical details of permanent failure: Google tried to deliver your message, but it was rejected by the server for the recipient domain spendsy.me by spendsy.me. [104.0.139.251]. The error that the other server returned was: 550 5.1.1 <devs@spendsy.me>: Recipient address rejected: User unknown in local recipient table ----- Original message ----- DKIM-Signature: v=1; a=rsa-sha256; c=relaxed/relaxed; d=gmail.com; s=20120113; h=from:content-type:content-transfer-encoding:subject:message-id:date :to:mime-version; bh=g3zLYH4xKxcPrHOD18z9YfpQcnk/GaJedfustWU5uGs=; b=0vxJv/BSwUc9C+v1GjIjdk2QgHg+HVEBpfwf0T4YNOH2EaDASil8+S7U5EOaH/RRpz exIDKukNMV+I9K712O5fMyazLyrZUBUpnS32t/BKcAyLFvTq1ZvW7qCIap295uWoh7CS /MVy+Tp0ndYOYl4BDFL1TSU1wIuqR7o+vfpOjU3SUbAVcEieU4rPTy2pudiAwAw72kiJ OvIAuQBpzDH5anfN0evdHb95967hlUSlTuorDSuMjkSBeyFF1+OPUyMbJD1BUns4vL7p JLJIzI7wBY359qx58T4s17O8qh4T+QCvJsT6qSMONrfw5Z1TYz8zbbGNc/d4sVoDjnmW MFKg== X-Received: by 10.182.22.201 with SMTP id g9mr11380434obf.75.1408482055402; Tue, 19 Aug 2014 14:00:55 -0700 (PDT) Return-Path: <cgjonesdev@gmail.com> Received: from [10.0.1.88] (65-36-10-51.static.grandenetworks.net. [65.36.10.51]) by mx.google.com with ESMTPSA id fu14sm30166524oeb.9.2014.08.19.14.00.54 for <devs@spendsy.me> (version=TLSv1 cipher=ECDHE-RSA-RC4-SHA bits=128/128); Tue, 19 Aug 2014 14:00:54 -0700 (PDT) From: Cary Jones <cgjonesdev@gmail.com> Content-Type: text/plain; charset=us-ascii Content-Transfer-Encoding: 7bit Subject: test Message-Id: <3806CA2F-FA2D-466F-924D-CEF788AB794B@gmail.com> Date: Tue, 19 Aug 2014 16:00:53 -0500 To: devs@spendsy.me Mime-Version: 1.0 (Mac OS X Mail 7.3 \(1878.6\)) X-Mailer: Apple Mail (2.1878.6) test | [7 empty] | None | [7 empty] | None |  | 0¦10008g: |  |  | None |  | Not started
Spendsy | SPEN-38 | Add requirements.txt files to app and api folders | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-19 11:10 |  | 2014-10-23 14:00 | 2014-10-23 13:57 |  |  | DevOps |  | 0 | 1 | [6 empty] | SPEN-66, SPEN-67 | [9 empty] | None | [7 empty] | None |  | 0¦100088: |  |  | None |  | Not started
Spendsy | SPEN-37 | Register Spendsy business name | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-19 08:24 |  | 2014-08-19 08:25 | 2014-08-19 08:25 |  |  | Admin |  | 0 | 1 | [8 empty] | Register business name and get tax ID/EIN for Spendsy | [7 empty] | None | [7 empty] | None |  | 0¦100080: |  |  | None |  | Not started
Spendsy | SPEN-36 | Copy Budgetwise code in Github over to Spendsy repo | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-19 08:21 |  | 2014-08-19 21:48 | 2014-08-19 08:21 |  |  | Admin, DevOps |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10007s: |  |  | None |  | Not started
Spendsy | SPEN-35 | As a user I should be able to see my budget for each income | Story | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-18 18:54 |  | 2014-08-28 17:23 |  |  |  | API, Web Application |  | 0 | 1 | [8 empty] | Currently, the app only allows you to see the budget for the primary income. In order to see the budget for other incomes, you would have to go to Incomes, set the primary income to the one you want to see, then view your budget for that income. This should happen automatically at the user's request with a drop-down selector. | [7 empty] | None | [7 empty] | None |  | 0¦10007k: |  |  | None |  | Not started
Spendsy | SPEN-34 | As a user I should be able to view and manage my bank accounts | Story | To Do | Blocker | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-18 18:53 |  | 2014-11-18 17:56 |  |  |  | API, Web Application |  | 0 | 1 | [5 empty] | SPEN-126, SPEN-127, SPEN-128, SPEN-129, SPEN-130 |  |  | Currently, there are only Users, Incomes, Expenses, and Transactions. Accounts should exist also and be tied to a User. Transactions should be tied to an Account. | [7 empty] | None | [7 empty] | None |  | 0¦10007c: |  |  | None |  | Not started
Spendsy | SPEN-33 | Burnrate monetary values not being updated | Bug | Done | Blocker | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-18 18:49 |  | 2014-08-28 19:13 | 2014-08-28 19:13 |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦100074: |  |  | None |  | Not started
Spendsy | SPEN-32 | Fix negative amounts for credits and postive amounts for debits in database | Bug | Done | Minor | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 22:00 |  | 2014-08-29 19:42 | 2014-08-29 19:16 |  |  | API, DevOps |  | 0 | 1 | [8 empty] | Create a script (or function in the interpreter) to check all the transaction amount signs and types. If the type is debit, the sign should be negative and if the type is credit, the sign should be invisible. When finished, updated the production database with the new values. | [7 empty] | None | [7 empty] | None |  | 0¦10006w: |  |  | None |  | Not started
Spendsy | SPEN-31 | Add tests that check the API using mock | Task | To Do | Critical | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 21:50 |  | 2014-08-28 18:04 |  |  |  | API |  | 0 | 1 | [8 empty] | http://www.toptal.com/python/an-introduction-to-mocking-in-python# http://www.voidspace.org.uk/python/mock/ https://wiki.python.org/moin/PythonTestingToolsTaxonomy#Mock_Testing_Tools https://www.youtube.com/watch?v=d3_LdLzWSXQ | [7 empty] | None | [7 empty] | None |  | 0¦10006o: |  |  | None |  | Not started
Spendsy | SPEN-30 | Make sure .gitignore file is configured correctly for spendsy | Task | Done | Critical | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 21:16 |  | 2014-08-19 21:48 | 2014-08-17 23:31 |  |  | DevOps |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10006g: |  |  | None |  | Not started
Spendsy | SPEN-29 | Research technologies for cloud hosting | Task | To Do | Trivial | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 21:02 |  | 2014-08-17 21:07 |  |  |  | Admin, DevOps |  | 0 | 1 | [8 empty] | https://console.developers.google.com/billing/redeem#7FMKLEPCDEPGYP http://aws.amazon.com/free/?sc_channel=PS&sc_campaign=AWS_Free_Tier_2013_T&sc_country=US&sc_publisher=Google&sc_medium=b_test_cloud_computing_bmm-web_services&sc_content=40951090362&sc_detail=%2Bamazon%20%2Bweb&sc_category=aws_cloud_computing&sc_segment=cloud_computing&sc_matchtype=b | [7 empty] | None | [7 empty] | None |  | 0¦100068: |  |  | None |  | Not started
Spendsy | SPEN-28 | SPEN-1 Create a Due template | Sub-task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 20:57 |  | 2014-08-17 20:57 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦100060: |  |  | None |  | Not started
Spendsy | SPEN-27 | SPEN-1 Create a "What's Due" link in the nav bar | Sub-task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 20:57 |  | 2014-11-18 17:40 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10005s: |  |  | None |  | Not started
Spendsy | SPEN-26 | SPEN-1 Update Due class logic in core.py | Sub-task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 20:56 |  | 2014-12-11 20:06 |  |  |  | API |  | 0 | 1 | [8 empty] | In web/api/core.py, there is a class called Due. The logic in this class is old and needs to be updated to use the api instead of old flat file storage. This included creating a new api endpoint called /due | [7 empty] | None | [7 empty] | None |  | 0¦10005k: |  |  | None |  | Not started
Spendsy | SPEN-25 | Optimize Web Application templates and stylesheet | Task | Done | Minor | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 20:51 |  | 2014-10-24 21:22 | 2014-10-24 21:22 |  |  | Web Application |  | 0 | 1 | [5 empty] | SPEN-5, SPEN-7, SPEN-72 | [10 empty] | None | [7 empty] | None |  | 0¦10005c: |  |  | None |  | Not started
Spendsy | SPEN-24 | SPEN-23 Research build systems | Sub-task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 20:47 |  | 2014-08-17 20:47 |  |  |  | Admin, DevOps |  | 0 | 1 | [8 empty] | http://jenkins-ci.org/ http://buildbot.net/ | [7 empty] | None | [7 empty] | None |  | 0¦100054: |  |  | None |  | Not started
Spendsy | SPEN-23 | Set up a build system | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 20:45 |  | 2014-08-17 21:02 |  |  |  | Admin, DevOps |  | 0 | 1 | [5 empty] | SPEN-24 | [10 empty] | None | [7 empty] | None |  | 0¦10004w: |  |  | None |  | Not started
Spendsy | SPEN-20 | SPEN-2 Remove "db." object usage in core.py and use the datamanager instead | Sub-task | In Review | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 18:49 |  | 2014-08-17 19:10 |  |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦100048: |  |  | None |  | Not started
Spendsy | SPEN-19 | SPEN-2 Remove "db." object usage in resources.py and use the datamanager instead | Sub-task | In Review | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 18:49 |  | 2014-08-17 18:55 |  |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦100040: |  |  | None |  | Not started
Spendsy | SPEN-18 | SPEN-2 Create a class in datamanager that generically handles mongo database specific logic | Sub-task | In Review | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 18:48 |  | 2014-08-17 18:55 |  |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10003s: |  |  | None |  | Not started
Spendsy | SPEN-17 | SPEN-2 Create a new file called datamanager.py | Sub-task | In Review | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 18:48 |  | 2014-08-17 18:55 |  |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10003k: |  |  | None |  | Not started
Spendsy | SPEN-16 | SPEN-15 Research OAuth to understand how it works | Sub-task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 15:01 |  | 2014-08-17 15:01 | [5 empty] | 0 | 1 | [8 empty] | https://developer.github.com/v3/oauth/ https://developer.github.com/v3/auth/#working-with-two-factor-authentication http://en.wikipedia.org/wiki/OAuth https://www.youtube.com/results?search_query=OAuth | [7 empty] | None | [7 empty] | None |  | 0¦10003c: |  |  | None |  | Not started
Spendsy | SPEN-15 | Connect DVCS Accounts in Jira to Github Spendsy account | Task | To Do | Minor | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:58 |  | 2014-08-17 21:08 |  |  |  | Admin |  | 0 | 1 | [5 empty] | SPEN-16 |  |  | Click here to connect DVCS Accounts to Github Spendsy: https://spendsy.atlassian.net/secure/admin/ConfigureDvcsOrganizations!default.jspa?source=devtools&selectHost=github#expand | [7 empty] | None | [7 empty] | None |  | 0¦100034: |  |  | None |  | Not started
Spendsy | SPEN-14 | SPEN-8 Implement Stripe's existing billing page or create a custom billing page | Sub-task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:42 |  | 2014-10-22 22:51 |  |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10002w: |  |  | None |  | Not started
Spendsy | SPEN-13 | SPEN-8 Create API endpoint to CRUD usage totals | Sub-task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:40 |  | 2014-08-17 14:40 |  |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10002o: |  |  | None |  | Not started
Spendsy | SPEN-12 | SPEN-8 Create interface for each API call from the Web Application to go through to accumulate usage total | Sub-task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:39 |  | 2014-08-17 14:39 |  |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10002g: |  |  | None |  | Not started
Spendsy | SPEN-11 | SPEN-8 Create logic to calculate what users will be charged for each api call | Sub-task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:38 |  | 2014-08-17 14:38 |  |  |  | API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦100028: |  |  | None |  | Not started
Spendsy | SPEN-10 | SPEN-8 Get and store Stripe API keys | Sub-task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:37 |  | 2014-08-17 14:37 |  |  |  | Admin, API |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦100020: |  |  | None |  | Not started
Spendsy | SPEN-9 | SPEN-8 Set up Stripe account for Spendsy | Sub-task | To Do | Major | Unresolved | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:36 |  | 2014-08-17 14:36 |  |  |  | Admin |  | 0 | 1 | [8 empty] | https://stripe.com/docs/api/python | [7 empty] | None | [7 empty] | None |  | 0¦10001s: |  |  | None |  | Not started
Spendsy | SPEN-8 | As a company Spendsy should be able to receive revenue from customers | Story | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:33 |  | 2014-08-17 21:05 |  |  |  | API |  | 0 | 1 | [5 empty] | SPEN-9, SPEN-10, SPEN-11, SPEN-12, SPEN-13, SPEN-14 | [10 empty] | None | [7 empty] | None |  | 0¦10001k: |  |  | None |  | Not started
Spendsy | SPEN-7 | SPEN-25 Move styling to static/style.css file | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:32 |  | 2014-10-24 21:22 | 2014-10-24 21:22 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10001c: |  |  | None |  | Not started
Spendsy | SPEN-6 | Burn rate tests need to be updated | Task | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:28 |  | 2014-09-02 18:19 |  |  |  | API |  | 0 | 1 | [7 empty] | Python, Flask virtualenv | Tests should check to make sure the calculations are correct. For example: 1) The suggested daily spending amount should equal the total spending amount for the pay period / the total number of days in the pay period. 1) If the average daily spending amount is $50, then the total amount spent / amount of time passed should equal 50. 2) If the percentage displayed for the amount spent is 35%, then the amount spent / the total amount to spend should equal .35 3) If the calculated burn rate is 50%, then the amount and percentage of money spent should be half the amount and percentage of the time passed for the pay period. 4) Check that the calculated percetages for days passed and money spent are correct based on given transactions inputs. | [7 empty] | None | [7 empty] | None |  | 0¦100014: |  |  | None |  | Not started
Spendsy | SPEN-5 | SPEN-25 Create templates for functional areas such as budget and burnrate | Sub-task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:16 |  | 2014-10-23 14:01 | 2014-10-23 14:01 |  |  | Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10000w: |  |  | None |  | Not started
Spendsy | SPEN-4 | Group membership and permission for /var/www on web server computer not working | Bug | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:09 |  | 2014-09-02 18:15 |  |  |  | DevOps |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10000o: |  |  | None |  | Not started
Spendsy | SPEN-3 | As I user I should be able to enter "Tithe" or "tithe" as an expense and have it auto-calculate 10% of my income | Story | To Do | Minor | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-17 14:00 |  | 2014-08-17 21:14 |  |  |  | API, Web Application |  | 0 | 1 | [16 empty] | None | [7 empty] | None |  | 0¦10000g: |  |  | None |  | Not started
Spendsy | SPEN-2 | Seperate Flask-restful backend code from mongodb calls into DataManager | Task | Done | Major | Done | Cary Jones [Administrator] | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-16 12:06 |  | 2014-08-27 23:22 | 2014-08-19 21:54 |  |  | API |  | 0 | 1 | _thumb_10000.png |  |  |  |  | SPEN-17, SPEN-18, SPEN-19, SPEN-20 | [10 empty] | None | [7 empty] | None |  | 0¦100008: |  |  | None |  | Not started
Spendsy | SPEN-1 | As a user I should be able to see a list of my upcoming expenses due | Story | To Do | Major | Unresolved | Unassigned | Cary Jones [Administrator] | Cary Jones [Administrator] | 2014-08-16 11:32 |  | 2014-08-17 20:58 |  |  |  | API, Web Application |  | 0 | 1 | [5 empty] | SPEN-26, SPEN-27, SPEN-28 | [10 empty] | None | [7 empty] | None |  | 0¦100000: |  |  | None |  | Not started
Generated at Wed Aug 03 15:05:13 CDT 2016 by Cary Jones [Administrator] using JIRA 1000.217.1#100008-sha1:fdd523c323c2c9db17acf28ef688f81d0a4b61ea.